## Sayfa1
Start Date 24/10/2024
Week |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
Procedural Steps | Current State | 17 February 2025 | 3 March 2025 | 10 March 2025 | 17 March 2025 | 24 March 2025 | 31 March 2025 | 7 April 2025 | 14 April 2025 | 21 April 2025 | 28 April 2025 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26
Project Work Plan Update | Completed | bar: Week 1 to Week 3
Literature Review Update | Completed | bar: Week 1 to Week 3
SRS Update | Completed | bar: Week 1 to Week 3
SDD Update | Completed | bar: Week 1 to Week 3
Test Plan Document | Continuing | bar: Week 3 to Week 5
Midterm Interactive Demo | Continuing | bar: Week 7
Final Product 1st Release | Continuing | bar: Week 1 to Week 10
User Manual | Continuing | bar: Week 11
Project Report | Continuing | bar: Week 12
Project Tracking Form | Continuing | bar: Week 12
Test Results | Continuing | bar: Week 12
Project Poster | Continuing | bar: Week 13
Updated Project Webpage | Continuing | bar: Week 13
Demo Video | Continuing | bar: Week 13
Presentation | Continuing | bar: Week 14