## Sayfa1
Start Date 24/10/2024
Week |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Procedural Steps | Current State | 30 September 2024 | 7 October 2024 | 14 October 2024 | 21 October 2024 | 28 October 2024 | 4 November 2024 | 11 November 2024 | 18 November 2024 | 25 November 2024 | 2 December 2024 | 9 December 2024 | 16 December 2024 | 23 December 2024 | 30 December 2024 | 6 January 2025 | 13 January 2025
Team Setup | Completed | bar: Week 1 to Week 2
Project Proposal Form | Completed | bar: Week 2
Project Selection Form | Completed | bar: Week 2
Project Work Plan | Completed | bar: Week 3 to Week 4
Literature Review | Continuing | bar: Week 4 to Week 6
Software Requirements Specification | Continuing | bar: Week 6 to Week 9
Project Webpage | Continuing | bar: Week 10 to Week 12
Software Design Description | Continuing | bar: Week 11 to Week 13
Project Report | Continuing | bar: Week 14 to Week 15
Presentation | Continuing | bar: Week 16